## Sheet 1 - ISMS-005_SoA_v0.1_202
ISMS-005_SoA_v0.1_2026-02-07
Control ID | Control Description (short) | Applicable (Y/N) | Justification | Implementation Status (Implemented/Partial/Planned) | Evidence IDs (EV-###) | Notes
A.5.19 | Supplier security requirements | Y | CloudFin relies on third-party SaaS and cloud providers; supplier security obligations are required | Planned |  | Will create supplier evaluation checklist + review record
A.5.21 | Managing information security in the ICT supply chain | Y | Supply-chain risks impact service delivery and data protection | Planned |  | Will define supplier onboarding + periodic review process
A.5.23 | Information security for use of cloud services | Y | Service is cloud-hosted; cloud security requirements and shared responsibility must be managed | Planned |  | Will define baseline cloud requirements + reviews
A.5.24 | Information security incident management planning and preparation | Y | Incidents must be handled consistently to reduce impact | Planned |  | Will create IR policy, roles, and runbook
A.5.25 | Assessment and decision on information security events | Y | Events must be triaged and classified to support correct response | Planned |  | Will create event triage criteria + ticket workflow
A.5.26 | Response to information security incidents | Y | Defined response steps are required for containment and recovery | Planned |  | Will create incident checklist + evidence templates
A.5.28 | Collection of evidence | Y | Incident evidence must be preserved for investigation and lessons learned | Planned |  | Will define evidence handling and retention
A.5.34 | Privacy and protection of PII | Y | Support tickets may contain PII; privacy controls are required | Planned |  | Will add data handling rules and retention
A.5.37 | Documented operating procedures | Y | Repeatable operations require documented procedures (deployments | access changes | backups) | Planned |  | Will create SOPs and link to evidence records
A.6.3 | Information security awareness | education and training | Y | Remote-first SaaS requires awareness to reduce phishing and misuse | Planned |  | Will create awareness material + training record EV
A.6.7 | Remote working | Y | Organization is remote-first; remote access and device expectations must be defined | Planned |  | Will create remote working policy and checks
A.7.1 | Physical security perimeter | N | No company-controlled office/facility in this scenario; remote-first | Not Applicable |  | Physical controls handled via remote working/device requirements
A.7.8 | Equipment siting and protection | N | No company-controlled data center or office equipment locations; cloud-hosted | Not Applicable |  | Physical environment security is provided by cloud supplier
A.8.2 | Privileged access rights | Y | Admin privileges exist (repo/admin | cloud); must be controlled | Planned |  | Will implement role review and approval records
A.8.3 | Information access restriction | Y | Access to data and systems must be restricted by role/need-to-know | Planned |  | Will define RBAC rules + access review evidence
A.8.4 | Access to source code | Y | Source code is critical; access must be restricted and monitored | Partial | EV-002; EV-004 | Branch protection + PR review implemented; need periodic access review record
A.8.5 | Secure authentication | Y | Strong authentication needed to reduce account takeover risk | Planned |  | Will enforce MFA for key systems and document settings
A.8.8 | Management of technical vulnerabilities | Y | Vulnerability identification and remediation is required for SaaS dependencies | Partial | EV-003 | Dependabot enabled; need remediation SLA + vuln tracking record
A.8.9 | Configuration management | Y | Configuration drift and misconfigurations are a major SaaS risk | Planned |  | Will define baseline configurations + change records
A.8.13 | Information backup | Y | Backups and restore testing required to ensure recovery | Planned |  | Will create backup schedule + restore test record
A.8.15 | Logging | Y | Logs needed for detection | investigation | and accountability | Planned |  | Will define logging requirements and retention
A.8.16 | Monitoring activities | Y | Monitoring and alerting needed to detect anomalies and incidents | Planned |  | Will define monitoring coverage + alert handling
A.8.24 | Use of cryptography | Y | Encryption is required to protect sensitive data in transit/at rest where applicable | Planned |  | Will document crypto standards and key management approach
A.8.25 | Secure development life cycle | Y | Secure SDLC required so security is built into features | Planned |  | Will document SDLC security stages
A.8.26 | Application security requirements | Y | Security requirements must be defined for app features and data access | Planned |  | Will add requirements checklist to PR/issue workflow
A.8.28 | Secure coding | Y | Secure coding reduces vulnerabilities in SaaS codebase | Planned |  | Will define coding standard + review checklist
A.8.29 | Security testing in development and acceptance | Y | Testing is required before release to prevent exploitable bugs | Planned |  | Will add SAST/DAST or checklist + evidence
A.8.31 | Separation of development | test and production environments | Y | Separation reduces accidental changes and data exposure | Planned |  | Will document environment separation and access rules
A.8.32 | Change management | Y | Controlled changes prevent unauthorized modifications and outages | Implemented | EV-002; EV-004 | Branch protection and PR-based change workflow enforced