## Sheet 1 - AUD-006_CAPA_Tracker_
AUD-006_CAPA_Tracker_v0.1_2026-02-07
CAPA ID | Related Finding ID | Requirement | Nonconformity Type (Major/Minor/OFI) | Problem Statement | Immediate Correction (Containment) | Root Cause | Corrective Action Plan | Owner | Due Date | Status | Verification Method | Effectiveness Verified By | Verification Date | Evidence IDs (EV-###)
CAPA-001 | F-001 | ISO 27001 Clause 6.2 | OFI | Information security objectives and measurement plan are not documented. | Create ISMS objectives document draft. | Not yet analyzed | Create ISMS-006 Objectives & Metrics with 6 measurable objectives (owner/metric/target/frequency). | Security/GRC (Badr) | 2026-02-21 | Open | Audit review of ISMS-006 completeness and linkage to risks/objectives. | Badr Karim
CAPA-002 | F-002 | ISO 27001 Clause 10.1 | Minor | Corrective action process and CAPA tracking are not established. | Create CAPA tracker and define workflow. | Not yet analyzed | Finalize AUD-006 tracker + add CAPA process section and ensure all findings are tracked to closure. | Security/GRC (Badr) | 2026-02-14 | Open | Verify CAPA process exists and is used for all findings. | Badr Karim
CAPA-003 | F-003 | ISO 27001 Clause 9.3 | OFI | Management Review template and schedule are not documented. | Draft management review template. | Not yet analyzed | Create ISMS-007 Management Review Template and schedule quarterly reviews aligned with AUD-001. | Management (Simulated) | 2026-02-21 | Open | Check management review template includes required inputs/outputs and first review record exists. | Badr Karim
CAPA-004 | F-004 | Annex A A.8.8 | Minor | Vulnerability remediation workflow/SLA tracking not documented (tool enabled only). | Create a simple vuln log and remediation SLA. | Not yet analyzed | Create Vulnerability Management Procedure + tracking log; create 1 sample vuln issue with triage and closure evidence. | Engineering Lead | 2026-02-21 | Open | Review procedure + verify at least one vulnerability ticket from detection to closure. | Badr Karim
CAPA-005 | F-005 | Annex A A.8.4 | OFI | No periodic access review record for repository permissions. | Perform initial repo access review and record it. | Not yet analyzed | Create Access Review Record template; perform repo access review and capture evidence. | Platform/DevOps Lead | 2026-02-21 | Open | Verify access review record exists and lists accounts/roles/approval. | Badr Karim